## Bug Report
Bug ID |  | Tên màn/chức năng | Tiêu đề | Mô tả | Yêu cầu | Các bước thực hiện | Trạng thái | Ngày tạo | Hình ảnh lỗi | Ngày đóng | Hình ảnh xác nhận đóng
Bug_1 | Common | List | Unified handling: Remove the sorting function by 'Status' column. |  | The 'Use a Custom Link' toggle is overlapping the description. |  | Open | 2025-05-07
Bug_2 | Locations | New (Add Location) | The 'Use a Custom Link' toggle is overlapping the description. | The 'Use a Custom Link' toggle is overlapping the description. |  |  | Close | 2025-05-02 | Use a Custom Link.PNG | 2025-05-03
Bug_3 |  | New (Add Location) | The FieldSet title should be stand out more. | FieldSet title not showing prominently | The FieldSet title should be stand out more. |  | Open | 2025-05-03 | Fields Set Title.png
Bug_4 |  | New (Add Location) | Title overlaps input field after saving content | Title overlaps input field after saving content |  |  | Open | 2025-05-03 | Title overlaps input field.mp4
Bug_5 |  | New (Add Location) | Change textarea resize to vertical only | Zooming in/out after resizing 'Location Description' causes UI errors. | Change textarea resize to vertical only |  | Open | 2025-05-03 | Bug Location Description.mp4
Bug_6 |  | Locations List / SORT | The sorting feature on this column is not relevant and should be removed |  | The sorting feature on this column is not relevant and should be removed |  | Open | 2025-05-03 | Sort.mp4
Bug_7 |  | Locations List | The content should be vertically centered. |  | The content should be vertically centered. |  | Open | 2025-05-03 | Adjust Locations List.png
Bug_8 |  | Locations List | Dropdown Options to Avoid | The dropdown currently contains options that should be removed. | Remove the first unnecessary option and replace it with a placeholder |  | Open | 2025-05-02 | DropDown Filter.PNG
Bug_9 |  | Locations List | Interface lacks consistency | Interface lacks consistency |  | 1. Open My Map Location > Locations 2. Sort by Title Check Reorder rows 3. Check My Map Location > Categories | Open | 2025-05-05 | Interface lacks consistency.png
Bug_10 |  | Locations List | Edit button is enable when locations are selected |  | Enable Edit button only when a single location is selected. |  | Open | 2025-05-06 | Edit button when locations are selected.mp4
Bug_11 |  | Locations List | 'Trash' Option to 'Actions' Dropdown | The "Trash" option is missing when filtering by "Published" or "Archived" |  |  | Open | 2025-05-06 | 'Trash' Option to 'Actions' Dropdown.png
Bug_12 |  | Import/Export | Add spacing between radio buttons |  | Add spacing between radio buttons |  | Open | 2025-05-06 | MML_Import-Export.png
Bug_13 |  | Statistics | UI bug in the Statistics screen |  | Date: Disable invalid dates in date picker - EndDate >= StartDate and vice versa. - Cannot select future dates Add spacing between search button and clear button Add spacing between the UI element is insufficient |  | Open | 2025-05-06 | MML_Statistics bug UI.png
Bug_14 | Custom Fields | Filter by Assigned Category | Filtering by Assigned Category is not working correctly |  |  |  | Open | 2025-05-07 | Dropdown Assigned Category.mp4
Open
Open
Bug_15 | Frontend | Frontend > location | The buttons are not functioning as expected. | The buttons are not functioning as expected. | - Create button wotrking - Increase the button size slightly for better visibility. - 'Edit Module' button does not overlap the menu content. |  | Pending | 2025-05-05 | Button is error.png | Ko test ở chế độ Login
Bug_16 |  | Frontend > location > Edit | Increase the button size slightly for better visibility | The button appears too small. | Increase the button size slightly for better visibility | 1. Open browser https://joomunitedtest.com/joomla/location/nt_thao_test-ui-ux-%5E.html 2. Login 3. Check button Edit | Pending | 2025-05-05 | The button appears too small..png
Bug_17 |  | Frontend > location > Edit | Make space between the two buttons | There is no space between the two buttons | Make space between the two buttons |  | Pending | 2025-05-05 | Frontend location editing.png

## CheckList
Joomla - My Map Locations
STT | Menu | Tên màn | Chức năng | Chức năng con | Trạng thái |  |  | Kết quả | Bug ID (Nếu có)
[5 empty] | Lần 1 | Lần 2 | Lần 3
1 | LOCATIONS | Add Location / Edit | Title | Tên tab | Pass |  |  | Pass
2 |  |  |  | tên màn | Pass |  |  | Pass
3 |  |  | Zoom in / Zoom out |  | Pass |  |  | Pass
4 |  |  | Zoom Maps |  | Fail |  |  | Failed
5 |  |  | Toolbar | Nội dung | Pass |  |  | Pass
6 |  |  |  | Màu sắc | Pass |  |  | Pass
7 |  |  | Title fieldset |  | Fail |  |  | Failed
8 |  |  | Name |  | Pass |  |  | Pass
9 |  |  | Alias |  | Pass |  |  | Pass
10 |  |  | Category |  | Pass |  |  | Pass
11 |  |  | Global Font Color |  | Pending |  |  | Pending
12 |  |  | Use a Custom Link |  | Fail |  |  | Failed
13 |  |  | Language |  | Pass |  |  | Pass
14 |  |  | Status |  | Pass |  |  | Pass
15 |  |  | Location description |  | Fail |  |  | Failed
16 |  |  | Tags |  | Pass |  |  | Pass
17 |  |  | Keywords |  | Pass |  |  | Pass
18 |  |  | Meta Description |  | Pass |  |  | Pass
19 |  |  | Google Place ID |  | Pass |  |  | Pass
20 |  |  | Created by |  | Pass |  |  | Pass
21 |  |  | Search field |  | Pass |  |  | Pass
22 |  |  | Latitude |  | Pass |  |  | Pass
23 |  |  | Longitude |  | Pass |  |  | Pass
24 |  |  | Address |  | Pass |  |  | Pass
25 |  |  | City |  | Pass |  |  | Pass
26 |  |  | State |  | Pass |  |  | Pass
27 |  |  | Country |  | Pass |  |  | Pass
28 |  |  | Zip code |  | Pending |  |  | Pending
29 |  |  | Contact Link | Input text | Pass |  |  | Pass
30 |  |  |  | Drop down | Pass |  |  | Pass
31 |  |  | Phone |  | Pending |  |  | Pending
32 |  |  | Hours |  | Pass |  |  | Pass
33 |  | Locations List | Button | New | Pass |  |  | Pass
34 |  |  |  | Edit | Fail |  |  | Failed
35 |  |  |  | Publish | Pass |  |  | Pass
36 |  |  |  | Unpublish | Pass |  |  | Pass
37 |  |  |  | Archive | Pass |  |  | Pass
38 |  |  |  | Check-in | Pass |  |  | Pass
39 |  |  |  | Trash | Pass |  |  | Pass
40 |  |  |  | Sync | Pass |  |  | Pass
41 |  |  |  | Options | Pass |  |  | Pass
42 |  |  | Dropdown | Paging | Pass |  |  | Pass
43 |  |  |  | Status | Pass |  |  | Pass
44 |  |  |  | Category | Pass |  |  | Pass
45 |  |  |  | Component | Pass |  |  | Pass
46 |  |  |  | Direction Table | Pending |  |  | Pending
47 |  |  |  | Sort by | Fail |  |  | Failed
48 |  |  | Paging |  | Pass
49 |  |  | Search field |  | Pass |  |  | Pass
50 |  |  | Result count |  | Fail |  |  | Failed
51 | CATEGORY | Categories List | Button | New | Pass |  |  | Pass
52 |  |  |  | Rebultd | Pass |  |  | Pass
53 |  |  |  | Clear | Pass
54 |  |  |  | Search | Pass |  |  | Pass
|  |  |  | Help | Pass
56 |  |  | Dropdown | Action | Pass |  |  | Pass
57 |  |  |  | Filter Options | Pass |  |  | Pass
58 |  |  |  | Status | Pass |  |  | Pass
59 |  |  |  | Access | Pass |  |  | Pass
60 |  |  |  | Tag | Pass |  |  | Pass
61 |  |  |  | Max Level | Pass |  |  | Pass
62 |  |  |  | Category | Pass |  |  | Pass
63 |  |  |  | Paging | Pass |  |  | Pass
64 |  |  |  | Ordering | Pass |  |  | Pass
65 |  |  |  | Columns | Pass |  |  | Pass
66 |  |  | Sort | Status | Pass |  |  | Pass
67 |  |  |  | Title | Pass |  |  | Pass
68 |  |  |  | Acess | Pass |  |  | Pass
69 |  |  |  | ID | Pass |  |  | Pass
70 |  |  | Ordering | sort | Pass |  |  | Pass
71 |  |  |  | Drap | Pass |  |  | Pass
72 |  | Add category | Title
73 |  |  | Alias
74 |  |  | Category | Description
75 |  |  |  | Pảent
76 |  |  |  | Sâttus
77 |  |  |  | Acess
78 |  |  |  | Tags
79 |  |  |  | Note
80 |  |  | Options | Layout
81 |  |  |  | Image
82 |  |  |  | image Description
83 |  |  |  | No Description
84 |  |  | Please select marker
85 |  |  | Publishing | Created Date
86 |  |  |  | Created By
87 |  |  |  | Modified Date
88 |  |  |  | Modified By
89 |  |  |  | Hits
90 |  |  |  | ID
91 |  |  |  | Meta Description
92 |  |  |  | Keywords
93 |  |  |  | Author
94 |  |  |  | Robots
95 |  |  | Permissions | Access List
96 |  |  |  | Acction column
97 |  |  |  | Select New Setting column
98 |  |  |  | Calulated Setting column
99 |  |  |  | Note
100 |  |  | Button | Save
101 |  |  |  | Cancel
102 |  |  |  | Save & close
103 |  |  |  | Save & new
104 | IMPORT/EXPORT |  | CSV Import | Text
105 |  |  |  | Input
106 |  |  |  | Radio
107 |  |  |  | Button
108 |  |  | CSV Automation synchronization | Text
109 |  |  |  | Dropdown
110 |  |  |  | Button
111 |  |  | KML Import
112 |  |  |  | Input file
113 |  |  |  | button
114 |  |  | Data Export
115 |  |  | Data maintenance
116 | CUSTOM FIELDS | Fields List | Button | New
117 |  |  |  | Clear
118 |  |  |  | Search
119 |  |  |  | Help
120 |  |  |  | Filter Options
121 |  |  |  | Colums
122 |  |  | Checkbox
123 |  |  | Dropdown | Status
124 |  |  |  | Field group
125 |  |  |  | Assigned
126 |  |  |  | Access
127 |  |  |  | Use in Subform
128 |  |  |  | Ordering
129 |  |  | Search field
130 |  | Add field | General | Type
131 |  |  |  | Name
132 |  |  |  | Labwl
133 |  |  |  | Description
134 |  |  |  | Requied
135 |  |  |  | Only Use in Subform
136 |  |  |  | Filter
137 |  |  |  | Maximum Length
138 |  |  |  | Status dropdown
139 |  |  |  | Field group
140 |  |  |  | Category
141 |  |  |  | Access
142 |  |  |  | Note
143 |  |  | Options | Placeholder
144 |  |  |  | Field Class
145 |  |  |  | Label Class (Form)
146 |  |  |  | Editable In
147 |  |  |  | Showon Attribute
148 |  |  |  | Display Class
149 |  |  |  | Value Class
150 |  |  |  | Show Label
151 |  |  |  | Label Class
152 |  |  |  | Automatic Display
153 |  |  |  | Prefix
154 |  |  |  | Suffix
155 |  |  |  | Layout
156 |  |  |  | Display When Read-Only
157 |  |  |  | Search Index
158 |  |  | Publishing | Created Date
159 |  |  |  | Created By
160 |  |  |  | Modified Date
161 |  |  |  | Modified By
162 |  |  |  | ID
163 |  |  | Permissions | Note
164 |  |  |  | Access List
165 |  |  |  | Action
166 |  |  |  | Select New Setting
167 |  |  |  | Calculated Setting
168 |  |  | Buttion | Toggle Inline Help | Fail |  |  | Failed
169 |  |  |  | Save
170 |  |  |  | Save & Close
171 |  |  |  | Save & New
172 |  |  |  | Cancel
173 |  |  | TITLE
174 | FIELD GROUP | List | Button | New
175 |  |  |  | Help
176 |  |  |  | Clear
177 |  |  |  | Option
178 |  |  |  | Filter option
179 |  |  |  | Column
180 |  |  | Dropdown | Actions
181 |  |  |  | Ordering
182 |  |  |  | paging
183 |  |  | Search field
184 |  |  | Sort | Order
185 |  |  |  | Status
186 |  |  |  | title
187 |  |  |  | Access
188 |  |  |  | ID
189 |  |  | Checkbox
190 |  | Add | General | Description
191 |  |  |  | Status
192 |  |  |  | Access
193 |  |  |  | Note
194 |  |  | Options
195 |  |  | Publishing | Created Date
196 |  |  |  | Created By
197 |  |  |  | Modified Date
198 |  |  |  | Modified By
199 |  |  |  | ID
200 |  |  | Permissions | Note
201 |  |  |  | Access List
202 |  |  |  | Action
203 |  |  |  | Select New Setting
204 |  |  |  | Calculated Setting
205 |  |  | Title
206 |  |  | Help
207 | Configuration | General configuration | Note
208 |  |  | Enable Statistics
209 |  |  | AJAX search
210 |  |  | Display Distance
211 |  |  | Unit of distance
212 |  |  | Map provider
213 |  |  | Autocomplete search
214 |  |  | Add Anywhere search
215 |  |  | Search anywhere by default
216 |  |  | Tag format in search
217 |  |  | Street view
218 |  |  | Display Route
219 |  |  | Route Format
220 |  |  | Contact links in location
221 |  |  | Contact button
222 |  |  | Target of contact link
223 |  |  | Map default zoom
224 |  |  | Height of the Map
225 |  |  | Width of the Map
226 |  |  | Information window height
227 |  |  | Information Window Width
228 |  |  | Distance for radius search
229 |  |  | Display distance select list
230 |  |  | Word crop in search results
231 |  |  | Load Jquery Sidebar
232 |  |  | Enable geolocation
233 |  |  | Display category filter
234 |  |  | Display country state filter
235 |  |  | Search by Zipcode
236 |  |  | Buttons color
237 |  |  | Global Font color
238 |  |  | Background image
239 |  |  | Show YOU marker
240 |  |  | You marker image
241 |  |  | Default icon image
242 |  |  | Helper Override
243 |  | Advanced display configuration | Note
244 |  |  | Fields
Map Providers
Rating and Comments
Joomla article location
Live update
Translations
245 |  | Permissions | Note
246 |  |  | Access List
247 |  |  | Action
248 |  |  | Select New Setting
249 |  |  | Calculated Setting

## My Ideas & Suggestions
Yêu cầu định dang/tính hợp lệ cho từng trường
| Name/Alias | Đang nhập đc tất cả các kí tự đặc biệt
| Phone | Chỉ nên nhập số và dấu +
| Hours | Không để định dạng textarea